## Fly
Project name | Model name | Vendor | PM | VAL | CPU | OS | Carrier | Country | MP date | Sample deadline | Sample Ready(yes/no) | Sample date | SW build ready date | Google Approval date(First sw version | Google Approval date(final build) | Note
IQ4405 | IQ4405_Quad | Ragentek | Joey | Vicky | MT6582M | 4.2.2 | Open market | Russia | 2014-Jan-24 | 2013-Dec-19 4pcs | yes | 2013-Nov-09 4pcs | 2013-Nov-27 | 2013-Dec-07 | 2014-Feb-07
IQ4402 | Era Style 1 | Konka | Molly | Tiger | MT6572 | 4.2.2 | Open market | Russia | 2014-Feb | 2014-Jan | no |  |  |  |  | 1st Launch date:2014-Jan-30,we can't do google certification. We can do it in next shipment
IQ4407 | Era Nano 7 | Konka | Molly | Tiger | MT6572AW | 4.2.2 | Open market | Russia | 2014-Feb-28 | 2014-Jan-15 2pcs | yes | 2014-Feb-21 | 2014-Apr-14 | 2014-Apr-24 |  | 14-1-15 confirm sw version, but the fingerprint format of final build is test-keys not release keys,so need get google approval for next sw version.
IQ4601 | IQ4601 | Huaqin | Kane | Vicky | MT6572AW | 4.2.2 | Open market | Russia | 2014-Mar-07 | 2014-Jan-23 4pcs | yes | 2014-Jan-12 4pcs | 2014-Jan-16 | 2014-Feb-07
IQ458 Quad | Evo Tech 2 | Konka | Molly | Tiger | MT6582M | 4.2.2 | Open market | Russia | 2014-Mar-13 | 2014-Feb-08 2pcs | yes | 2014-Feb-28 2pcs（update the new samples for camera) | 2014-Feb-25 |  | 2014-Mar-05 | SW07
IQ456 | Era Life 2 | Konka | Molly | Tiger | MT6572AW | 4.2.2 | Open market | Russia | 2014-Mar-31 | 2014-Feb-09 2pcs | yes | 2014-Feb-12 2pcs | 2014-Mar-13 |  | 2014-Mar-25 | SW05
IQ4501 Quad | Evo Energie 4 | Gionee | Molly | Tiger | MT6582V/X | 4.2.2 | Open market | Russia | 2014-Mar-14 | 2014-Feb-09 2pcs | yes | 2014-Feb-27 2pcs | 2014-Mar-18 |  | 2014-Mar-25 | SW09
IQ459 Quad | Evo Chic 2 | Konka | Molly | Tiger | MT6582 | 4.2.2 | Open market | Russia | 2014-Mar-19 | 2014-Feb-14 4pcs | yes | 2014-Jan-27 3pcs 2014-Feb-19 1pcs Update camera HW at 2014-Feb-28 | 2014-Feb-25 | 2014-Mar-05 |  | SW05
IQ459 | IQ459 | Konka | Rita | George | MT6582 | 4.4.2 | Open market | Turkey | 2014-Oct-30 | 2014-Sep-30 1pcs | yes | 2014-Oct-10 | 2014-Oct-21 |  | 2014-Nov-14 | SW14
IQ4410i | IQ4410i | Gionee | Molly | Tiger | MT6582V/X | 4.2.2 | Open market | Russia | 2014-Mar-24 | 2014-Feb-19 4pcs | yes | 2014-Feb-17 4pcs | 2014-Mar-29 |  | 2014-Apr-01
IQ4406 | Fly Era Nano 6 | FSJ | Joey | Vicky | MT6572AW | 4.2.2 | Open market | Russia | 2014-May-09 | 2014-Apr-20 2pcs | yes | 2014-Apr-10 | 2014-Apr-21 | 2014-Apr-24 |  | SW06
Flylife Connect 7.85 3G 2 | Flylife Connect 7.85 3G 2 | SGW | Joey | Vicky | MT8382V/X | 4.2.2 | Open market | Russia | 2014-Apr-03 | 2014-Feb-28 4pcs | yes | 2014-Mar-06 4pcs | 2014-Mar-06 | 2014-Mar-18 |  | SW05
IQ455 Octa | Fly Ego Art 2 | SGW | Joey | Vicky | MT6592 | 4.2.2 | Open market | Russia | 2014-Apr-20 | 2014-Mar-04 4pcs | yes | 2014-Apr-04 4pcs | 2014-Apr-18 | 2014-Apr-24 |  | SW06
Flylife Connect 7 3G 2 | Flylife Connect 7 3G 2 | SGW | Joey | Vicky | MT8312 | 4.2.2 | Open market | Russia | 2014-Apr-09 | 2014-Mar-04 4pcs | yes | 2014-Mar-10 4pcs | 2014-Mar-21 | 2014-Apr-24 |  | SW07
Flylife Connect 10.1 3G 2 | Flylife Connect 10.1 3G 2 | SGW | Joey | Vicky | MT8382V/W | 4.2.2 | Open market | Russia | 2014-Apr-22 | 2014-Mar-17 4pcs | yes | 2014-Apr-10 | 2014-Apr-22 | 2014-Apr-24 |  | SW06
IQ4491 Quad | IQ4491 Quad | Sprocomm | Kane | Tiger | BCM 23550 | 4.2 | Open market | Ukraine | 2014-May-19 | 2014-Apr-15 | no |  |  |  |  | Android 4.2 is expired at Apr-24th-2014, the schedule can't catch the time
IQ4400 | IQ4400 | Tigel | Kane | Vicky | MT6571 | 4.4 | Open market | Russia | 2014-Jul-25 | 2014-Jun-25 4 pcs | yes | 2014-Jun-24 | 2014-Jul-31 |  | 2014-Aug-21 | SW09
IQ4400 | Fly Iris | Tigel | Rita | George | MT6571 | 4.4 | Open market | Africa | 2014-Sep-14 | 2014-Aug-14 1pcs | yes | 2014-Sep-16 | 2014-Sep-17 |  | 2014-Oct-16 | SW03
IQ434 | IQ434 | FSN | Mandy | Vicky | MT6571AE | 4.4 | Open market | Russia | TBC | TBC 4pcs | yes | 2014-Oct-15 | 2014-Oct-27 |  | 2014-Nov-27 | V05
IQ4401 | IQ4401 | Tigel | Kane | Vicky | MT6572M(X) | 4.4 | Open market | Russia | 2014-Aug-22 | 2014-Jul-22 4pcs | yes | 2014-Jul-03 | 2014-Aug-12 | 2014-Aug-29 |  | SW06
IQ4413 | IQ4413 | Regantek | Joey | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-May-30 | 2014-May-20 2pcs | yes | 2014-May-13 | 2014-Jun-09 2014-Jul-22 resubmit |  | 2014-Jul-30 | SW08
IQ4415 Quad | Fly Era Style 3 | Konka | Molly | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-May-01 | 2014-Apr-01 2pcs | yes | 2014-Apr-23 | 2014-May-19 |  | 2014-Jun-02 | SW07
IQ4415 Quad | IQ4415 | Konka | Rita | George | MT6582M | 4.4 | Open market | Africa | 2014-Oct-30 | 2014-Sep-30 1pcs | yes | 2014-Oct-17 | 2014-Oct-28 |  | 2014-Nov-14 | SW05
IQ4416 | IQ4416 | Konka | Molly | Tiger | MT6572AW | 4.2 | Open market | Russia | 2014-May-01 | 2014-Apr-01 2pcs | yes | 2014-Apr-11 | 2014-Apr-16 | 2014-Apr-24 |  | SW03
IQ4409 Quad | Fly Era life4 | Regantek | Joey | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-Jun-11 | 2014-May-18 2pcs | yes | 2014-Jun-06 | 2014-Jun-09 |  | 2014-Jul-30 | SW07
IQ4414 | Fly Evo Tech3 | Longcheer | Mandy | Tiger | MT6582 | 4.4 | Open market | Russia | 2014-Jun-30 | 2014-May-30 2pcs | yes | 2014-Apr-28 | 2014-Jul-22 |  |  | SW14
IQ4502 Quad | IQ4502 Quad | Longcheer | Mandy | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-Jun-27 | 2014-May-20 2pcs | yes | 2014-May-14 | 2014-Jul-24 |  | 2014-Jul-31 | SW10
IQ436i | IQ436i | Sprocomm | Kane | Tiger | SC7715 | 4.4 | Open market | Russia | 2014-Aug-10 | 2014-Jul-10 4pcs | yes | 2014-Aug-04 | 2014-Aug-18 |  | 2014-Sep-09 | SW08
IQ4490i | IQ4490i | Sprocomm | Kane | Tiger | SC7715 | 4.4 | Open market | Russia | 2014-Aug-30 | 2014-Jul-30 2pcs | yes | 2014-Aug-30 | 2014-Sep-01 |  | 2014-Sep-18 | SW07
IQ4511 octa | IQ4511 Octa | Regantek | Joey | Tiger | MT6592M | 4.4 | Open market | Russia | 2014-Jul-30 | 2014-Jun-30 4pcs | yes | 2014-Aug-20 | 2014-Aug-25 |  | 2014-Oct-16 | SW07
IQ4417 Quad | IQ4417 Quad | Konka | Molly | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-Aug-20 | 2014-Jul-20 2pcs | yes | 2014-Jul-29 | 2014-Aug-12 |  | 2014-Aug-15 | SW07
IQ4513 Octa | IQ4513 Octa | CKT | Molly | Tiger | MT6592 | 4.4 | Open market | Russia | 2014-Sep-24 | 2014-Aug-24 2pcs | yes | 2014-Jul-30 | 2014-Sep-01 |  | 2014-Sep-15 | SW08
IQ4513 | IQ4513 | CKT | James | Spring | MT6592T | 4.4 | Open market | Turkey | 2014-Sep-10 | 2014-Aug-10 4pcs | yes | 2014-Aug-27 | 2014-Sep-29 |  | 2014-Nov-14 | SW06
IQ4503Q | IQ4503Q | Sprocomm | Kane | Tiger | BCM23550 | 4.4 | Open market | Russia | 2014-Sep-05 | 2014-Aug-01 2pcs | yes | 2014-Aug-18 | 2014-Sep-25 |  | 2014-Oct-11 | SW10
IQ4503 | FLY IQ4503 | Sprocomm | James | Spring | BCM23550 | 4.4 | Open market | Africa | 2014-Oct-10 | 2014-Sep-10 1pcs | yes | 2014-Aug-18 | 2014-Sep-26 |  | 2014-Oct-16 | SW07
IQ4503 | FLY IQ4503 | Sprocomm | James | Spring | BCM23550 | 4.4 | Open market | MEA | 2014-Oct-30 | 2014-Sep-30 1pcs | yes | 2014-Aug-18 | 2014-Oct-29 |  | 2014-Oct-29 | SW03
IQ4512 Quad | IQ4512 Quad | Sprocomm | Kane | Tiger | BCM23550 | 4.4 | Open market | Russia | 2014-Aug-26 | 2014-Jul-30 2pcs | yes | 2014-Jul-11 | 2014-Sep-16 |  | 2014-Oct-11 | SW13
IQ4418 | IQ4418 | Konka | Molly | Tiger | MT6572M | 4.4 | Open market | Russia | 2014-Sep-06 | 2014-Aug-06 2pcs | yes | 2014-Aug-14 | 2014-Aug-21 |  | 2014-Aug-21 | SW05
IQ4418 | IQ4418 | Konka | Rita | George | MT6572M | 4.4 | Open market | Africa | 2014-Sep-15 | 2014-Aug-15 1pcs | yes | 2014-Sep-15 | 2014-Sep-15 | 2014-Sep-15 |  | SW02
IQ4514 Quad | IQ4514 Quad | Konka | Molly | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-Sep-30 | 2014-Aug-30 2pcs | yes | 2014-Sep-03 | 2014-Sep-17 |  | 2014-Oct-11 | SW05
IQ4514 Quad | IQ4514 Quad | Konka | Rita | George | MT6582M | 4.4 | Open market | Africa | 2014-Oct-30 | 2014-Sep-30 1pcs | yes | 2014-Oct-15 | 2014-Oct-20 |  | 2014-Oct-20 | SW04
IQ4504 Quad | IQ4504 Quad | Konka | Molly | Tiger | MT6582M | 4.4 | Open market | Russia | 2014-Sep-30 | 2014-Aug-30 2pcs | yes | 2014-Sep-03 | 2014-Sep-15 |  | 2014-Oct-11 | SW03
IQ4505 | IQ4505 | CG Mobile | Joey | Vicky | SC7731 | 4.4 | Open market | Russia | 2014-Nov-15 | 2014-Oct-15 4pcs | yes | 2014-Oct-09 | 2014-Oct-23 | 2014-Nov-25 |  | SW04/SW07
IQ4516 | IQ4516 | Gionee | Molly | Tiger | MT6592 | 4.4 | Open market | Russia | 2014-Oct-30 | 2014-Sep-30 2pcs | yes | 2014-Oct-15 | 2014-Oct-16/2014-Oct-28 |  | 2014-Oct-22/28 | SW07/SW08
IQ4602 | Fly Evo Chic 5 | Gfive | Mandy | Tiger | MT6582 | 4.4 | Open market | Russia | 2014-Dec-01 | 2014-Nov-01 2pcs | yes | 2014-Oct-15 | 2014-Nov-21 |  | 2014-Dec-01 | SW08
IQ4602 | IQ4602 | Gfive | Andy | Eric | MT6582 | 4.4 | Open market | MEA | 2014-Nov-27 | 2014-Oct-27 1pcs | yes | 2014-Nov-12 | 2014-Nov-28 |  | 2014-Dec-01 | SW08
IQ4602 | IQ4602 | Gfive | Andy | Eric | MT6582 | 4.4 | Open market | Iran | 2015-Mar-10 | 2015-May 1pcs | yes | 2015-Mar-01 | 2015-Mar-09 |  | 2015-Mar-09 | SW01
IQ4515 Quad | IQ4515 Quad | Billionwell | Mandy | Tiger | MT6582 | 4.4 | Open market | Russia | 2014-Nov-20 | 2014-Oct-20 2pcs | yes | 2014-Sep-12 | 2014-Nov-07 |  | 2014-Nov-10 | SW08/SW10
IQ455 | Fly Tornado 1 | SGW | Rita | Spring | MT6592 | 4.2 | Open market | Africa | 2014-Sep-15 | 2014-Aug-15 2pcs | no |  |  |  |  | 4.2 is expired for google certification
IQ4516 | IQ4516 | Gionee | James | Spring | MT6592 | 4.4 | Open market | MEA | 2014-Nov-07 | 2014-Oct-07 1 pcs | yes | 2014-Oct-21 | 2014-Nov-06 | 2014-Nov-07 |  | SW04/SW06
IQ4505 | IQ4505 | CG Mobile | Andy | Eric | SC7731 | 4.4 | Open market | MEA | 2014-Nov-27 | 2014-Oct-27 1pcs | yes | 2014-Nov-11 | 2014-Dec-01 |  | 2014-Dec-08 | SW04
IQ4490i | IQ4490i | Sprocomm | James | Spring | SC7715 | 4.4 | Open market | MEA | 2014-Oct-30 | 2014-Sep-30 1pcs | yes | 2014-Oct-08 | 2014-Oct-28 |  | 2014-Oct-28 | SW03
IQ4511 | IQ4511 | Regantek | Andy | Eric | MT6592M | 4.4 | Open market | Turkey | 2014-Dec-16 | 2014-Nov-30 2pcs | yes | 2014-Nov-18 | 2014-Dec-17 |  | 2014-Dec-18 | SW01
IQ4511 | IQ4511 | Regantek | Andy | Eric | MT6592M | 4.4 | Open market | Iran | 2015-Jan-19 | NA | NA |  | 2015-Jan-21 |  | 2014-Jan-22 | SW03
IQ4421 Quad | IQ4421 Quad | Kingcomm | Joey | Tiger | MT6582V/X | 4.4 | Open market | Russia | 2015-Jan-26 | 2014-Dec-26 2pcs | yes | 2014-Dec-30 | 2015-Jan-28 | 2015-Feb-09 |  | SW07
IQ4514 | IQ4514 | Konka | Rita | George | MT6582M | 4.4 | Open market | Iran | 2015-Feb-02 | NA | NA |  | 2014-Dec-30 |  |  | SW10
IQ4509 | IQ4509 | Billionwell | Rita | George | MT6592 | 4.4 | Open market | Turkey | 2015-Feb | 2015-Jan 2pcs | yes | 2015-Jan-15 | 2015-Jan-28 | 2015-Feb-09 |  | SW06
IQ4509 | IQ4509 | Billionwell | Rita | George | MT6592 | 4.4 | Open market | Africa | 2015-Feb | 2015-Jan 1pcs | yes | 2015-Jan-15 | 2015-Jan-28 | 2015-Feb-09 |  | SW06
IQ4509 | IQ4509 | Billionwell | Rita | George | MT6592 | 4.4 | Open market | MEA | 2015-Apr | NA | NA
IQ4507 | IQ4507 | FSN | James | Spring | SC7731 | 4.4 | Open market | MEA | 2015-May | 2015-Apr 2pcs | yes | 2015-Mar-27 | 2015-Apr-15 | 2015-Apr-27 |  | SW06
FS551 | Nimbus 4 | FSN | Mandy | Vicky | SC7731 | 4.4 | Open market | Russia | 2015-May | 2015-Apr 2pcs | yes |  | 2015-May-12 |  |  | SW06
IQ4551 | IQ4551 | FSN | James | Spring | SC7731 | 4.4 | Open market | MEA | 2015-May | 2015-Apr 2pcs | yes |  | 2015-Apr-27 | 2015-May-07 |  | SW03
IQ4508 | IQ4508 | Huiye | Rita | George | SC7731 | 4.4 | Open market | MEA | 2015-May | 2015-Apr 2pcs | yes |  | 2015-Apr-29 |  |  | SW05
IQ4508 | IQ4508 | Huiye | Rita | George | SC7731 | 4.4 | Open market | Africa | 2015-May | NA | no |  |  | 2015-May-14 |  | SW02
FS451 | Nimbus 1 | Sprocomm | Kane | Janny | SC7731 | 4.4 | Open market | Russia | 2015-Jun | 2015-May-2pcs | yes |  | 2015-May-12 |  |  | SW03
FS452 | FS452 | Kingcomm | Joey | Janny | SC7731 | 4.4 | Open market | Russia | 2015-Jun | 2015-May-2pcs | yes |  | 2015-May-18 | 2015-June-10 |  | SW04
FS401 | Stratus 1 | Sprocomm | Kane | Janny | SC7715 | 4.4 | Open market | Russia | 2015-Jun | 2015-May-2pcs | yes |  | 2015-May-13 |  |  | SW05
FS501 | Nimbus 3 | Sprocomm | Kane | Janny | SC7731 | 4.4 | Open market | Russia | 2015-Jun | 2015-May-2pcs | yes |  | 2015-May-11 |  |  | SW04
FS502 | Cirrus 1 | CG Mobile | Joey | Vicky | SC7731 | 5.1 | Open market | Russia | 2015-July | 2015-Jun-2pcs | yes |  | 2015-Jul-17 | 2015-Aug-05 |  | SW05
FS504 | Cirrus 2 | Frog | Kane | Mark | MT6580 | 5.1 | Open market | Russia | 2015-Oct-14 | 2015-Aug 4pcs | yes |  | 2015-Sep-08 | 2015-Sep-21 |  | SW04
FS402 | Stratus 2 | Kingcomm | Mandy | Vicky | MT6572AW | 5.1 | Open market | Russia | 2015-Nov | 2015-Oct 2pcs | yes |  | 2015-Oct-16 |  |  | SW06
FS404 | Stratus 3 | FSN | Mandy | Vicky | MT6572 | 5.1 | Open market | Russia | 2016-Mar | 2016-Feb 3pcs | yes |  |  |  |  | SW10
FS505 | Nimbus 7 | FSN | Mandy | Vicky | MT6580M | 5.1 | Open market | Russia | 2016-Mar | 2016-Feb 2pcs | yes |  |  |  |  | SW08
FS454 | Nimbus 8 | FSN | Mandy | Vicky | MT6580M | 6 | Open market | Russia | 2016-May | 2016-Mar 2pcs | yes |  |  | 2016-06-30 | 2016-08-10 | first build
FS506 | Cirrus 3 | Sprocomm | Kane | Mark | MT6580A | 5.1 | Oepn market | Russia | 2016-May | 2016-Mar 2pcs | yes |  |  | 2016-Apr-25 |  | SW07
FS405 | Stratus 4 | Frog | Kane | Mark | MT6572A | 5.1 | Open market | Russia | 2016-Apr | 2016-Feb 2pcs | yes |  |  | 2016-04-13 |  | SW06
FS507 | Cirrus 4 | Frog | Kane | Mark | MT6580A | 6 | Open market | Russia | 2016-Apr | 2016-Feb 2pcs | yes |  |  | 2016-Apr-26 | 2016-07-25 | SW09
FS406 (4+512) | Stratus 5 | Kingcomm | Mandy | Vicky | SC7731C | 6 | Open market | Russia | 2016-Jul | 2016-May 4pcs | yes | 2016-07-05 | 2016-08-03 | 2016-08-10 |  | first build
FS407 4+512 | Stratus 6 | FSN | Mandy | Alice | SC7731C | 6 | Open market | Russia | 2016-08-27 | 2016-July 2pcs | yes |  | 2016-08-04 | 2016-08-10 |  | First build
FS508 (8+1) | Cirrus 6 | Kingcomm | Mandy | Vicky | MTK6580 | 6 | Open market | Russia | 2016-08-23 | 2016-June 2pcs | yes
FS509 (8+1) | Nimbus 9 | Kingcomm | Mandy | Vicky | MT6580A/M | 6 | Open market | Russia | 2016-08-12 | 2016-June 2pcs | yes
FS512 (8+1) | Nimbus 10 | FSN | Mandy | Alice | MT6735P | 6 | Open market | Russia | 2016-09-29 | 2016-June 4pcs | yes
FS455 （8+1） | Nimbus 11 | FSN | Mandy | Alice | MT6737M | 6 | Open market | Russia | 2016-09-15 | 2016-July 4pcs(2) | yes
FS514 (8+1) | Cirrus 8 | Frog | Kane | Mark | MT6580A | 6 | Open market | Russia | 2016-09-14 | 2016-July 2pcs | yes
FS511 (16+2) | Cirrus 7 | Kozen | Kane | Mark | MT6737 | 6 | Open market | Russia | 2016-09-28
FS510 （8+1） | Nimbus 12 | Sprocomm | Kane | Mark | MT6580A | 6 | Open market | Russia | 2016-10-12 | 2016-Aug 2pcs | yes
FS553 | Cirrus 9 | Kozen | Kane | Mark | MT6737 | 6 | Open market | Russia | 2016-10-19

## Wileyfox
Project name | Model name | Vendor | PM | VAL | CPU | OS | Carrier | Country | Launch date | Sample deadline | Sample Ready(yes/no) | Sample date | SW build ready date | Google Approval date(First sw version | Google Approval date(final build) | Note
Swift | Swift | Longcheer | Mandy | Grant | MSM8916 | CM5.1 | Open market | All | 2015-July-24th | June-24th | yes
Storm | Storm | CKT | Joey | Fred | MSM8939 | CM5.1 | Open market | All | 2015-Aug-15th | July-15th | yes |  |  |  | 2015-Oct-16 | YOG4PAS33I
Spark | Spark | Xinyi | Jeffery | Grant | MT6735A | Android 6.0.1 | Open market | All | 2016-Apr-25th | 2016-Mar | yes |  |  |  | 2016-06-22 | ZNH0EAS3UH
Spark X（16+2） | Spark X | Xinyi | Jeffery | Grant | MT6735A | Android 6.0.1 | Open market | All | 2016-07-18 |  | yes | 2016-June
Swift2 plus(32+3) | Swift2 plus | HY | Beryl | Alice | MSM8937 | Android 6.0.1 | Open market | All | 2016-09-26
Swift2 (16+2) | Swift2 | HY | Beryl | Alice | MSM8937 | Android 6.0.1 | Open market | All
Swift2 X | Swift2 x | HY | Beryl | Flora | MSM8937 | Android 6.0.1 | Open market | All

## Google_approval
Device | Brand | Fingerprint | SW version | Google approval status | Submission date | Approval Date | Comment
IQ4405_Quad | Fly | fly/IQ4405_Quad/IQ4405_Quad:4.2.2/JDQ39/1385549971:user/release-keys | SW06_FLY_IQ4405_2013_11_27 | Approval | 2013-Nov-29 | 2013-Dec-07 | First sw version
IQ4405_Quad | Fly | fly/IQ4405_Quad/IQ4405_Quad:4.2.2/JDQ39/1388138787:user/release-keys | SW11_FLY_IQ4405_2013_12_27 | Approval | 2014-Jan-24 | 2014-Feb-07 | Final build
IQ4601 | Fly | Fly/IQ4601/IQ4601:4.2.2/FlyIQ4601/SW04_FLY_IQ4601_2014_01_16:user/release-keys | SW04_FLY_IQ4601_2014_01_16 | Approval | 2014-Jan-24 | 2014-Feb-07 | First sw version
IQ459 Quad | Fly | Fly/IQ459/IQ459:4.2.2/JDQ39/eng.JB5.1393398480:user/release-keys | SW06_FLY_IQ459_2014_02_25 | Approval | 2014-Feb-28 | 2014-Mar-05 | First sw version
IQ458 Quad | Fly | Fly/IQ458/IQ458:4.2.2/JDQ39/eng.JB5.1393290860:user/release-keys | SW07_FLY_IQ458_2014_02_25 | Approval | 2014-Feb-28 | 2014-Mar-05 | Final build
Flylife Connect 7.85 3G 2 | Fly | Fly/Flylife/Flylife:4.2.2/JDQ39/1392982282:user/release-keys | SW05_Flylife_connect_7.85_3G_2_2014_03_03 | Approval | 2014-Mar-07 | 2014-Mar-18 | First sw version
KAZAM Trooper2 40 | KAZAM | KAZAM/Trooper2_40/Trooper2_40:4.2.2/JDQ39/1394198065:user/release-keys | SW07_KAZAM_Trooper2_4.0_2014_03_07 | Approval | 2014-Mar-10 | 2014-Mar-18 | Final build
KAZAM Trooper2 60 | KAZAM | KAZAM/A1800/Trooper2_60:4.2.2/KAZAMA1800/SW10_KAZAM_Trooper2_6.0_2014_3_8:user/release-keys | SW10_KAZAM_Trooper2_6.0_2014_3_8 | Approval | 2014-Mar-11 | 2014-Mar-18 | Final build
IQ456 | Fly | Fly/IQ456/IQ456:4.2.2/JDQ39/eng.Fly.1394710981:user/release-keys | SW05_FLY_IQ456_2014_03_13 | Approval | 2014-Mar-17 | 2014-Mar-25 | Final build
KAZAM THUNDER2 45L | KAZAM | KAZAM/Thunder2_45/Thunder2_45:4.3/JLS36C/20140305.182117:user/release-keys | SW09_KAZAM_THUNDER2_45L_2014_03_13 | Approval | 2014-Mar-21 | 2014-Apr-23 | First sw version
Evo Energy4 | KAZAM | Fly/Fly/IQ4501:4.2.2/JDQ39/1393919824:user/release-keys | SW09_FLY_Evo Energy4_2014_03_18 | Approval | 2014-Mar-25 | 2014-Mar-25 | Final build
Phoenix 2 | Fly | Fly/Fly/IQ4410i:4.2.2/JDQ39/1393987245:user/release-keys | SW_FLY_Phoenix 2_2014_03_18 | Approval | 2014-Mar-31 | 2014-Apr-01 | Final build
T700 | Toughshield | Toughshield/T700_TABLET/T700_TABLET:4.2.2/JDQ39/V00.00:user/release-keys | MTK6589_R2412_TS_T700_GMS_R2413_140402 | Approval | 2014-Apr-04 | 2014-Apr-23 | Final build
KAZAM Trooper2 50 | KAZAM | KAZAM/Trooper2_50/Trooper2_50:4.2.2/JDQ39/1396444657:user/release-keys | SW06_KAZAM_Trooper2_5.0_2014_04_02 | Approval | 2014-Apr-04 | 2014-Apr-15 | First sw version
Trooper2 45 | KAZAM | KAZAM/Trooper2_45/Trooper2_45:4.2.2/JDQ39/1397195865:user/release-keys | SW07_KAZAM_Trooper2_4.5_2014_04_10 | Approval | 2014-Apr-15 | 2014-Apr-23 | First sw version
KAZAM Tornado2 50 | KAZAM | KAZAM/Tornado2_50/Tornado2_50:4.2.2/JDQ39/1396621214:user/release-keys | SW06_KAZAM_Tornado2_5.0_2014_04_04 | Approval | 2014-Apr-15 | 2014-Apr-24 | First sw version
IQ4407 | Fly | Fly/IQ4407/Fly_IQ4407:4.2.2/JDQ39/eng.Fly.1397470705:user/release-keys | SW08_FLY_IQ4407_2014_04_14 | Approval | 2014-Apr-16 | 2014-Apr-24 | First sw version
IQ4416 | Fly | Fly/IQ4416/IQ4416:4.2.2/JDQ39/eng.Fly.1397640223:user/release-keys | SW03_FLY_IQ4416_2014_04_16 | Approval | 2014-Apr-17 | 2014-Apr-24 | First sw version
IQ4406 | Fly | FLY/Era_Nano_6/Era_Nano_6:4.2.2/JDQ39/1397732038:user/release-keys | SW06_FLY_IQ4406_2014_04_17 | Approval | 2014-Apr-21 | 2014-Apr-24 | First sw version
Fly Ego Art 2 | Fly | Fly/Fly_Ego_Art_2/Fly_Ego_Art_2:4.2.2/JDQ39/1397628585:user/release-keys | SW06_FLY_IQ455_Octa_2014_04_12 | Approval | 2014-Apr-18 | 2014-Apr-24 | First sw version
Flylife Connect 7 3G 2 | Fly | Fly/Flylife7/Flylife7:4.2.2/JDQ39/1396533392:user/release-keys | SW07_Flylife_Connect_7_3G_2_2014_03_21 | Approval | 2014-Apr-17 | 2014-Apr-24 | First sw version
KAZAM Thunder2 50 | KAZAM | KAZAM/Thunder2_50/Thunder2_50:4.2.2/JDQ39/1397630945:user/release-keys | SW07_KAZAM_Thunder2_5.0_2014_04_16 | Approval | 2014-Apr-18 | 2014-Apr-24 | First sw version
IQ4415 Quad | Fly | Fly/IQ4415_Quad/IQ4415_Quad:4.4.2/KOT49H/1398747224:user/release-keys | SW07_FLY_IQ4415_2014_04_29 | Approval | 2014-May-20 | 2014-Jun-02 | Final build
IQ4413_Quad | Fly | Fly/IQ4413_Quad/IQ4413_Quad:4.4.2/KOT49H/1401161552:user/release-keys | SW08_FLY_IQ4413_2014_07_21 | Approval | 2014-Jul-22 resumbit | 2014-Jul-30 | Final build
IQ4409 Quad | Fly | Fly/IQ4409_Quad/IQ4409_Quad:4.4.2/KOT49H/1402321709:user/release-keys | SW07_FLY_IQ4409_2014_06_09 | Approval | 2014-Jul-28 resumbit | 2014-Jul-30 | Final build
IQ4414 Quad | Fly | Fly/Fly_Evo_Tech_3/IQ4414_Quad:4.4.2/KOT49H/1399864822:user/release-keys | SW14_FLY_IQ4414_Quad_2014_07_14 | Approval | 2014-Jul-22 | 2014-Aug-02 | Final build
IQ4502 Quad | Fly | Fly/Fly_Era_Energy_1/IQ4502_Quad:4.4.2/KOT49H/1401430963:user/release-keys | SW10_FLY_IQ4502_Quad_2014_06_23 | Approval | 2014-Jul-24 | 2014-Jul-29 | Final build
IQ4400 | Fly | Fly/Fly_Era_Nano_8/IQ4400:4.4.2/KOT49H/1398747224:user/release-keys | SW09_FLY_IQ4400_2014_07_25 | Approval | 2014-Jul-31 | 2014-Aug-21 | Final build
Thunder 347 | KAZAM | KAZAM/KAZAM_Thunder_347/Thunder_347:4.4.2/KOT49H/1399864822:user/release-keys | SW07_KAZAM_Thunder_347_2014_07_29 | Approval | 2014-Aug-01 | 2014-Aug-07 | Final build
KAZAM Thunder 345 | KAZAM | KAZAM/Thunder_345/Thunder_345:4.4.2/KOT49H/1406788090:user/release-keys | SW09_KAZAM_Thunder_345_2014_07_31 | Approval | 2014-Aug-04 | 2014-Aug-04 | Final build
KAZAM Thunder 345 LTE | KAZAM | KAZAM/Thunder_345_LTE/Thunder_345_LTE:4.4.2/KOT49H/1407478625:user/release-keys | SW06_KAZAM_Thunder_345_LTE_2014_08_08 | Approval | 2014-Aug-11 | 2014-Aug-15 | Final build
Thunder3 45LTE | KAZAM | KAZAM/Thunder_345_LTE/Thunder_345_LTE:4.4.2/KOT49H/1408107792:user/release-keys | SW06_KAZAM_Thunder_345_LTE_2014_08_08 | Approval | 2014-Aug-19 | 2014-Aug-19 | Final build
IQ4417 Quad | Fly | Fly/IQ4417_Quad/IQ4417_Quad:4.4.2/KOT49H/1398747224:user/release-keys | SW07_FLY_IQ4417_2014_08_07 | Approval | 2014-Aug-12 | 2014-Aug-15 | Final build
IQ4401 | Fly | Fly/IQ4401/IQ4401:4.4.2/KOT49H/1405917955:user/release-keys | SW06_FLY_IQ4401_2014_08_08 | Approval | 2014-Aug-13 | 2014-Aug-29 | First sw version
IQ436i | Fly | Fly/IQ436i/IQ436i:4.4.2/KOT49H/1407333367:user/release-keys | SW08_FLY_IQ436i_2014_08_13 | Approval | 2014-Aug-18 | 2014-Sep-09 | First sw version
IQ4418 | Fly | Fly/IQ4418/IQ4418:4.4.2/KOT49H/1407720933:user/release-keys | SW05_FLY_IQ4418_2014_08_19 | Approval | 2014-Aug-21 | 2014-Aug-21 | Final build
IQ4418 | Fly | Fly/IQ4418/IQ4418:4.4.2/KOT49H/1409304651:user/release-keys | SW02_FLY_IQ4418AF_2014_08_29 | Approval | 2014-Sep-15 | 2014-Sep-15 | First sw version
IQ4511 Octa | Fly | Fly/IQ4511_Octa/IQ4511_Octa:4.4.2/KOT49H/1408096231:user/release-keys | SW07_FLY_IQ4511_Octa_2014_08_15 | Approval | 2014-Aug-25 | 2014-Oct-16 | Final build
KAZAM TV 45 | KAZAM | KAZAM/KOT49H/KOT49H:4.4.2/KOT49H/20140803.163429:user/release-keys | SW10_KAZAM_TV_45_2014_08_25 | Approval | 2014-Aug-27 | 2014-Sep-09 | FOTA
IQ4513 Octa | Fly | Fly/IQ4513_Octa/IQ4513_Octa:4.4.2/KOT49H/1398847224:user/release-keys | SW08_FLY_IQ4513_Octa_2014_08_29 | Approval | 2014-Sep-01 | 2014-Sep-15 | Final build
IQ4490i | Fly | Fly/IQ4490i/IQ4490i:4.4.2/KOT49H/1408701233:user/release-keys | SW07_FLY_IQ4490i_2014_08_22 | Approval | 2014-Sep-02 |  | Final build
KAZAM Thunder 345L | KAZAM | KAZAM/Thunder_345L/Thunder_345L:4.4.2/KOT49H/1407919736:user/release-keys | SW07_KAZAM_Thunder_345L_2014_08_27 | Approval | 2014-Sep-03 | 2014-Sep-15 | Final build
KAZAM Tornado 350 | KAZAM | KAZAM/KAZAM_Tornado_350/KAZAM_Tornado_350:4.4.2/KOT49H/1409553859:user/release-keys | SW04_KAZAM_Tornado_350_2014_09_01 | Approval | 2014-Sep-05 | 2014-Sep-11 | Frist version
KAZAM Tornado 350 | KAZAM | KAZAM/KAZAM_Tornado_350/KAZAM_Tornado_350:4.4.2/KOT49H/1410856222:user/release-keys | SW06_KAZAM_Tornado_350_2014_09_16 | Approval | 2014-Sep-18 | 2014-Sep-18 | Final build
R200 | Toughshield | Toughshield/R200/R200:4.4.2/KOT49H/1409021743:user/release-keys | SW19_R200_2014_08_26 | Approval | 2014-Sep-09 | 2014-Sep-12 | Final build
KAZAM Thunder 350L | KAZAM | KAZAM/Thunder_350L/Thunder_350L:4.4.2/KOT49H/1409912994:user/release-keys | SW04_KAZAM_Thunder_350L_2014_09_05 | Approval | 2014-Sep-11 | 2014-Sep-11 | Frist version
KAZAM Thunder 350L | KAZAM | KAZAM/Thunder_350L/Thunder_350L:4.4.2/KOT49H/1411549773:user/release-keys | SW06_KAZAM_Thunder_350L_2014_09_26 | Approval | 2014-Sep-26 | 2014-Sep-26 | Final build
KAZAM TV 45 | KAZAM | KAZAM/TV_45/TV_45:4.4.2/KOT49H/20140803.163429:user/release-keys | SW10_KAZAM_TV_45_2014_08_28 | Approval | 2014-Sep-11 | 2014-Sep-15 | FOTA
IQ4504 Quad | Fly | Fly/IQ4504/IQ4504_Quad:4.4.2/KOT49H/1410504042:user/release-keys | SW03_FLY_IQ4504_2014_09_12 | Approval | 2014-Sep-15 | 2014-Oct-11 | Frist version
IQ4512 Quad | Fly | Fly/IQ4512_Quad/IQ4512_Quad:4.4.2/KOT49H/1409664875:user/release-keys | SW13_FLY_IQ4512Quad_2014_09_11 | Approval | 2014-Sep-16 | 2014-Oct-11 | Final build
FLY_IQ4400_AF | Fly | FLY_IQ4400/Fly_Iris/FLY_IQ4400:4.4.2/KOT49H/1398747235:user/release-keys | SW03_FLY_IQ4400AF_2014_09_10 | Approval | 2014-Sep-17 | 2014-Oct-16 | Final build
IQ4514 Quad | Fly | Fly/IQ4514/IQ4514_Quad:4.4.2/KOT49H/1410511290:user/release-keys | SW05_FLY_IQ4514_2014_09_12_CTS | Approval | 2014-Sep-17 | 2014-Oct-11 | First sw version
IQ4503 Quad | Fly | Fly/IQ4503_Quad/IQ4503_Quad:4.4.2/KOT49H/20140903.204315:user/release-keys | SW10_FLY_IQ4503Quad_20140921 | Approval | 2014-Sep-25 | 2014-Oct-11 | Final build
FLY IQ4503 | Fly | Fly/IQ4503/IQ4503:4.4.2/KOT49H/1411547318:user/release-keys | SW07_FLY_IQ4503AF_2014_09_25 | Approval | 2014-Sep-26 | 2014-Oct-16 | Final build
IQ4513 | Fly | Fly/IQ4513/IQ4513:4.4.2/KOT49H/1398847224:user/release-keys | SW06_FLY_TR_IQ4513_2014_09_24 | Approval | 2014-Sep-29 | 2014-Nov-14 | Final build
IQ4516 Octa | Fly | Fly/IQ4516_Octa/IQ4516_Octa:4.4.2/KOT49H/1413200279:user/release-keys | SW07_FLY_IQ4516 Octa_2014_10_13 | Approval | 2014-Oct-15 | 2014-Oct-22 | First sw version
IQ4516 Octa | Fly | Fly/IQ4516_Octa/IQ4516_Octa:4.4.2/KOT49H/1414054265:user/release-keys | SW08_FLY_IQ4516 Octa_2014_10_23 | Approval | 2014-Oct-28 | 2014-Oct-28 | Final build
Tornado 348 | KAZAM | KAZAM/Tornado_348/Tornado_348:4.4.2/KOT49H/1413191554:user/release-keys | SW05_KAZAM_Tornado_348_2014_10_13 | Approval | 2014-Oct-16 | 2014-Oct-22 | First sw version
Tornado 348 | KAZAM | KAZAM/Tornado_348/Tornado_348:4.4.2/KOT49H/1414078579:user/release-keys | SW06_KAZAM_Tornado_348_2014_10_23 | Approval | 2014-Oct-28 | 2014-Oct-29 | Final build
Fly IQ4514 AF | Fly | Fly/IQ4514/IQ4514_Quad:4.4.2/KOT49H/1413513447:user/release-keys | SW04_FLY_IQ4514AF_2014_10_16 | Approval | 2014-Oct-20 |  | First sw version
IQ459 | Fly | Fly/IQ459/IQ459:4.4.2/KOT49H/eng.JB5.1411121324:user/release-keys | SW14_FLY_TR_IQ459_2014_10_20 | Approval | 2014-Oct-21 | 2014-Nov-14 | Final build
IQ4505 Quad | Fly | Fly/FlyIQ4505/IQ4505_Quad:4.4.2/KOT49H/20140927.004535:user/release-keys | SW04_FLY_IQ4505 Quad_2014_10_11 | Approval | 2014-Oct-23 | 2014-Nov-25 | First sw version
IQ434 | Fly | Fly/IQ434/IQ434:4.4.2/KOT49H/1414148868:user/release-keys | V530_02B_CFZZ_IQ434_Y2F_BT_FM_GS_WIFI_GPS_SC_V05 | Approval | 2014-Oct-27 | 2014-Nov-27 | Final build
IQ4490i | Fly | Fly/IQ4490i/IQ4490i:4.4.2/KOT49H/1408701234:user/release-keys | SW03_FLY_IQ4490iME_2014_10_25 | Approval | 2014-Oct-28 | 2014-Oct-29 | Final build
IQ4415 | Fly | Fly/IQ4415/IQ4415:4.4.2/KOT49H/1414029280:user/release-keys | SW05_FLY_IQ4415AF_2014_10_23 | Approval | 2014-Oct-28 | 2014-Nov-14 | Final build
FLY IQ4503 | Fly | Fly/IQ4503/IQ4503:4.4.2/KOT49H/1411547319:user/release-keys | SW03_FLY_IQ4503ME_2014_10_24 | Approval | 2014-Oct-29 | 2014-Oct-30 | Final build
IQ4516 | Fly | Fly/IQ4516_Octa/IQ4516_Octa:4.4.2/KOT49H/1414603446:user/release-keys | SW04_FLY_IQ4516 Octa_2014_10_30 | Approval | 2014-Nov-06 | 2014-Nov-07 | Final build
IQ4515 Quad | Fly | Fly/IQ4515_Quad/IQ4515_Quad:4.4.2/KOT49H/eng.maizhitao.1415168411:user/release-keys | SW10_FLY_IQ4515_2014_11_05 | Approval | 2014-Nov-07 | 2014-Nov-10 | Final build
IQ4515 Quad | Fly | Fly/IQ4515_Quad/IQ4515_Quad:4.4.2/KOT49H/eng.maizhitao.1414033213:user/release-keys | SW08_FLY_IQ4515_2014_10_23 | Approval | 2014-Nov-10 | 2014-Nov-10 | Final build
Tornado 348 | KAZAM | KAZAM/Tornado_348/Tornado_348:4.4.2/KOT49H/1416237800:user/release-keys | SW04_KAZAM_Tornado_348_2014_11_17 | Approval | 2014-Nov-19 | 2014-Nov-20 | Final build
IQ4516 | Fly | Fly/IQ4516_Octa/IQ4516_Octa:4.4.2/KOT49H/1415790032:user/release-keys | SW06_FLY_IQ4516 _2014_11_12 | Approval | 2014-Nov-19 | 2014-Nov-19 | Final build
IQ4602 Quad | Fly | Fly/IQ4602_Quad/IQ4602_Quad:4.4.2/KOT49H/1410511290:user/release-keys | SW08_FLY_IQ4602_Quad_2014_11_20 | Approval | 2014-Nov-21 | 2014-Dec-01 | Final build
IQ4505 Quad | Fly | Fly/FlyIQ4505/IQ4505_Quad:4.4.2/KOT49H/20141023.004535:user/release-keys | SW07_FLY_IQ4505 Quad_2014_10_27 | Approval | 2014-Nov-25 | 2014-Nov-25 | Final build
KAZAM Trooper 450 | KAZAM | KAZAM/KAZAM_Trooper_450/KAZAM_Trooper_450:4.4.2/KOT49H/1416639711:user/release-keys | SW02_KAZAM_Trooper_450_Telefonica_2014_11_22 | Approval | 2014-Nov-25 | 2014-Dec-01 | Final build
KAZAM Trooper 450 | KAZAM | KAZAM/KAZAM_Trooper_450/KAZAM_Trooper_450:4.4.2/KOT49H/1416980148:user/release-keys | SW06_KAZAM_Trooper_450_2014_11_26 | Approval | 2014-Dec-01 | 2014-Dec-02 | Final build
Fly IQ4602 | Fly | Fly/Fly_IQ4602/Fly_IQ4602:4.4.2/KOT49H/1410511290:user/release-keys | SW08_FLY_IQ4602ME_2014_11_25 | Approval | 2014-Nov-28 | 2014-Dec-01 | Final build
Fly IQ4505 | Fly | Fly/FlyIQ4505/IQ4505:4.4.2/KOT49H/1399864822:user/release-keys | SW04_FLY_IQ4505ME_2014_11_24 | Approval | 2014-Dec-01 | 2014-Dec-08 | Final build
KAZAM Trooper 451 | KAZAM | KAZAM/Trooper_451/Trooper_451:4.4.2/KOT49H/1399864822:user/release-keys | SW02_KAZAM_Trooper_451_2014_12_05 | Approval | 2014-Dec-01 | 2014-Dec-18 | First sw version
IQ4511 TR | Fly | Fly/IQ4511_Octa/IQ4511_Octa:4.4.2/KOT49H/1415632827:user/release-keys | SW01_FLY_TR_IQ4511_2014_12_12 | Approval | 2014-Dec-17 | 2014-Dec-18 | First sw version
KAZAM Trooper 440L | KAZAM | KAZAM/Trooper_440L/Trooper_440L:4.4.2/KOT49H/1419848383:user/release-keys | SW05_KAZAM_Trooper_440L_2014_12_29 | Approval | 2014-Dec-31 | 2015-Jan-05 | First sw version
KAZAM Tornado 455L | KAZAM | KAZAM/KAZAM_Tornado_455L/KAZAM_Tornado_455L:4.4.4/KTU84P/31:user/release-keys | SW04_KAZAM_TORNADO_455L_2015_01_13 | Approval | 2015-Jan-15 | 2015-Feb-02 | First sw version
IQ4421 Quad | Fly | Fly/IQ4421_Quad/IQ4421_Quad:4.4.2/KOT49H/1422004079:user/release-keys | SW07_FLY_IQ4421_Quad_2015_01_23 | Approval | 2015-Jan-28 | 2015-Feb-09 | First sw version
IQ4509 | Fly | Fly/IQ4509/IQ4509:4.4.2/KOT49H/eng.longyanliang.1419673216:user/release-keys | SW06_FLY_TR_IQ4509_2015_01_19 | Approval | 2015-Jan-28 | 2015-Feb-09 | First sw version
KAZAM Trooper 450L | KAZAM | KAZAM/KAZAM_Trooper_450L/KAZAM_Trooper_450L:4.4.4/KTU84P/20150202.171251:user/release-keys | SW08_KAZAM_Trooper_450L_2015_02_02 | Approval | 2015-Feb-05 | 2015-Feb-13 | First sw version
Fly IQ4602 | Fly | Fly/Fly_IQ4602/Fly_IQ4602:4.4.2/KOT49H/1410511291:user/release-keys | SW01_FLY_IQ4602MEA_OPEN_2015_03_05 | Approval | 2015-Mar-09 | 2015-Mar-10 | First sw version
KAZAM Trooper 445L | KAZAM | KAZAM/Trooper_445L/TR4L4544:4.4.2/KOT49H/1426155124:user/release-keys | SW09_KAZAM_Trooper_445L_2015_03_13 | Approval | 2015-Mar-20 | 2015-Apr-03 | First sw version
KAZAM Trooper 455 | KAZAM | KAZAM/Trooper_455/TR45544:4.4.2/KOT49H/1399864833:user/release-keys | SW05_KAZAM_Trooper_455_2015_03_17 | Approval | 2015-Apr-03 | 2015-Apr15 | First sw version
IQ4507 | Fly | Fly/IQ4507/Dune_3:4.4.2/KOT49H/1428890198:user/release-keys | SW06_FLY_IQ4507MEA_ES_2015_04_13 | Approval | 2015-Apr-15 | 2015-Apr-27 | First sw version
KAZAM Trooper 540 | KAZAM | KAZAM/KAZAM_Trooper_540/TR54015:4.4.2/KOT49H/1428991100:user/release-keys | SW02_KAZAM_Trooper_540_2015_04_14 | Approval | 2015-Apr-16 | 2015-Apr-27 | First sw version
IQ4551 | Fly | Fly/IQ4551/Epic_Note:4.4.2/KOT49H/1429774169:user/release-keys | SW03_FLY_IQ4551MEA_ES_2015_04_23 | Approval | 2015-Apr-27 | 2015-May-07 | First sw version
Fly IQ4508 | Fly | Fly/IQ4508/Dune_4:4.4.2/KOT49H/1430106268:user/release-keys | SW05_FLY_IQ4508MEA_ES_2015_04_27 | Approval | 2015-Apr-29 | 2015-May-12 | First sw version
KAZAM Trooper 550 | KAZAM | KAZAM/KAZAM_Trooper_550/TR55015:4.4.2/KOT49H/20150428.175243:user/release-keys | SW04_KAZAM_Trooper_550_2015_04_28 | Approval | 2015-Apr-30 | 2015-May-13 | First sw version *
KAZAM Trooper 551 | KAZAM | KAZAM/Trooper_551/TR550115:4.4.2/KOT49H/1429732769:user/release-keys | SW02_KAZAM_Trooper_551_2015_04_23 | Approval | 2015-Apr-30 | 2015-May-12 | First sw version
FS501 | Fly | Fly/FS501/Nimbus3:4.4.2/KOT49H/1432130644:user/release-keys | SW04_Fly_FS501_20150520 | Approval | 2015-May-11 |  | First sw version
FS451 | Fly | Fly/FS451/Nimbus1:4.4.2/KOT49H/1432124561:user/release-keys | SW04_Fly_FS451_20150520 | Approval | 2015-May-12 |  | First sw version
FS551 | Fly | Fly/FS551/Nimbus_4:4.4.2/KOT49H/1432521458:user/release-keys | SW08_FLY_FS551_2015_05_25 | Approval | 2015-May-12 |  | First sw version
FS401 | Fly | Fly/FS401/Stratus1:4.4.2/KOT49H/1432282257:user/release-keys | SW05_Fly_FS401_20150522 | Approval | 2015-May-13 |  | First sw version
FS452 | Fly | Fly/FS452/Nimbus_2:4.4.2/KOT49H/20150514.175358:user/release-keys | SW04_FLY_FS452_2015_05_13 | Approval | 2015-May-18 |  | First sw version
KAZAM Trooper 555 | KAZAM | KAZAM/KAZAM_Trooper_555/TR55515:4.4.2/KOT49H/20150520.112050:user/release-keys | SW01_KAZAM_Trooper_555_2015_05_20 | Approval | 2015-May-21 |  | First sw version
KAZAM Thunder 550 | KAZAM | KAZAM/Thunder_550/TH55025:4.4.2/KOT49H/eng.guanqiu.20150520.114238:user/release-keys | SW02_KAZAM_Thunder_555_2015_05_20 | Approval | 2015-May-21 |  | First sw version
FS502 | Fly | Fly/FlyFS502/Cirrus_1:5.1/LMY47D/20150716.142729:user/release-keys | SW05_Fly_FS502_20150717 | Approval | 2015-Jul-17 |  | First sw version
KAZAM Thunder 550L | KAZAM | KAZAM/Thunder_550L/TH5L5025:5.1/LMY47D/1437567287:user/release-keys | SW07_KAZAM_Thunder_550L_2015_07_17 | Approval | 2015-Jul-31 | 2015-Aug-19 | First sw version
KAZAM Trooper 550L | KAZAM | KAZAM/Trooper_550L/TR5L5025:5.1/LMY47D/1434636836:user/release-keys | SW05_KAZAM_Trooper_550L_2015_07_14 | Approval | 2015-Jul-31 | 2015-Aug-18 | First sw version
KAZAM Trooper 545 | KAZAM | KAZAM/KAZAM_Trooper_545/TR54525:5.1/LMY47D/07271649:user/release-keys | SW05_KAZAM_Trooper_545_2015_07_27 | Approval | 2015-Aug-07 | 2015-Aug-25 | First sw version
Wileyfox swift | Wileyfox | Wileyfox/Swift/crackling:5.1.1/LMY48B/YOG4PAS1T1:user/release-keys | YOG4PAS1T1 | Approval | 2015-Sep-02 | 2015-Sep-24 | Final build
FS504 | Fly | Fly/FS504/Cirrus_2:5.1/LMY47I/04:user/release-keys | SW04_FLY_FS504_2015_09_02 | Approval | 2015-Sep-08 |  | First sw version
FS402 | Fly | Fly/FS402/Stratus_2:5.1/LMY47I/1444386338:user/release-keys | SW06_FLY_FS402_2015_10_08 | Approval | 2015-Oct-16 |  | First sw version
Wileyfox Storm | Wileyfox | Wileyfox/Storm/kipper:5.1.1/LMY48B/YOG4PAS33I:user/release-keys | YOG4PAS33I | Approval | 2015-Oct-12 | 2015-Oct-16 | Final build
KAZAM Trooper 555 | KAZAM | KAZAM/KAZAM_Trooper_555/TR55515:5.1/LMY47D/12101608:user/release-keys | SW10_KAZAM_Trooper_555_LP_2015_12_07 | Approval | 2015-Dec-14 |  | First sw version
KAZAM Trooper 650 4G | KAZAM | KAZAM//Trooper_650_4G/TR6L5035:5.1/LMY47V/eng.root20160222.163302:user/release-keys | SW02_KAZAM_Trooper4G_Virgin_2016_02_22 | Approval | 2016-Feb-23 |  | First sw version-Virgin
KAZAM Trooper 650 4G | KAZAM | KAZAM//Trooper_650_4G/TR6L5035:5.1/LMY47V/eng.root20160224.205519:user/release-keys | SW04_KAZAM_Trooper4G_2016_02_24 | Approval | 2016-Mar-10 |  | Final build
FS404 | Fly | Fly/FS404/Stratus_3:5.1/LMY47I/1457939858:user/release-keys | SW10_FLY_FS404_2016_03_13 | Approval | 2016-Mar-16 | 2016-Mar-29 | First sw version
FS404 | Fly | Fly/FS404/Stratus_3:5.1/LMY47I/1457874641:user/release-keys | SW09_FLY_FS404_2016_03_13 | Approval | 2016-Mar-30 | 2016-Mar-30 | Final build
FS505 | Fly | Fly/FS505/Nimbus_7:5.1/LMY47I/1457408542:user/release-keys | SW08_FLY_FS505_2016-03-08 | Approval | 2016-Mar-14 | 2016-Mar-29 | First sw version
FS505 | Fly | Fly/FS505/Nimbus_7:5.1/LMY47I/1457779695:user/release-keys | SW10_Fly_FS505_2016-03-12 | Approval | 2016-Mar-30 | 2016-Mar-30 | Final build
FS405 | Fly | Fly/FS405/Stratus_4:5.1/LMY47I/1459128941:user/release-keys | SW6_FLY_FS405_20160328 | Approval | 2016-Mar-30 | 2016-Apr-13 | First sw version
FS405 | Fly | Fly/FS405/Stratus_4:5.1/LMY47I/1460371504:user/release-keys | SW08_FLY_FS405_20160411 | Approval | 2016-Apr-13 | 2016-Apr-14 | Final build
FS506 | Fly | Fly/FS506/Cirrus_3:5.1/LMY47I/1461227115:user/release-keys | SW07_FLY_FS506_2016_04_21 | Approval | 2016-Apr-25 | 2016-May-04 | SW07
KAZAM Trooper 650 | KAZAM | KAZAM/Trooper_650/TR65035:5.1/LMY47I/1460724768:user/release-keys | SW05_KAZAM_Trooper_650_2016_04_15 | Approval | 2016-Apr-19 | 2016-04-26 | SW05
Spark | Wileyfox | Wileyfox/Spark/porridge:6.0.1/MMB29X/ZNH0EAS3UH:user/release-keys | ZNH0EAS3UH | Approval | 2016-06-05 | 2016-06-22 | MP1
Spark | Wileyfox | Wileyfox/Spark/porridge:6.0.1/MMB29X/ZNH0EAS4SF:user/release-keys | ZNH0EAS4SF | Approval | 2016-07-16 | 2016-07-22 | MP2
Spark | Wileyfox | Wileyfox/Spark/porridge:6.0.1/MMB29X/ZNH0EAS58C:user/release-keys | ZNH0EAS58C | Approval | 2016-07-25 | 2016-07-25 | OTA
Spark | Wileyfox | Wileyfox/Spark/porridge:6.0.1/MMB29X/ZNH0EAS6MA:user/release-keys | ZNH0EAS6MA | Approval | 2016-09-12 | 2016-09-12 | OTA
Storm | Wileyfox | Wileyfox/Storm/kipper:6.0.1/MMB29X/ZNH0EAS45F:user/release-keys | ZNH0EAS45F | Approval | 2016-06-17 | 2016-06-21 | FOTA
Swift | Wileyfox | Wileyfox/Swift/crackling:6.0.1/MMB29X/ZNH0EAS3PL:user/release-keys | ZNH0EAS3PL | Approval | 2016-06-01 | 2016-06-07 | FOTA
FS507 | Fly | Fly/FS507/Cirrus_4:6.0/MRA58K/1463657936:user/release-keys | SW11_FLY_FS507_2016_05_19 | Approval | 2016-07-01 | 2016-07-25 | MP
Swift | Wileyfox | Wileyfox/Swift/crackling:6.0.1/MHC19Q/ZNH2KAS29G:user/release-keys | ZNH2KAS29G | Approval | 2016-07-11 | 2016-08-02 | 13.1 FOTA
FS454 | Fly | Fly/FS454/Nimbus_8:6.0/MRA58K/1463452037:user/release-keys | SW09_FLY_FS454_2016_05_17 | Approval | 2016-08-02 | 2016-08-10 | MP1
FS454 | Fly | Fly/FS454/Nimbus_8:6.0/MRA58K/1465196305:user/release-keys | SW12_FLY_FS454_2016_06_06 | Approval | 2016-08-04 | 2016-08-10 | MP2
FS407 | Fly | Fly/FS407/Stratus_6:6.0/MRA58K/W16.30.5-17:user/release-keys | sw08 | Approval | 2016-08-04 | 2016-08-10 | MP
FS406 | Fly | Fly/FS406/Stratus_5:6.0/MRA58K/W16.28.5-15:user/release-keys | SW09_FLY_FS406_2016_07_20 | Approval | 2016-08-03 | 2016-08-10 | MP

## Kazam
Project name | Model name | Vendor | PM | VAL | CPU | OS | Carrier | Country | Launch date | Sample deadline | Sample Ready(yes/no) | Sample date | SW build ready date | Google Approval date(First sw version | Google Approval date(final build) | Note
Trooper X3.5 | Trooper X3.5 | Mobiwire | Michael | Fred | MT6572M | 4.2.2 |  |  | 2014-Feb | 2014-Jan-01 | no |  |  |  |  | 1st Launch date: 2013-Nov
Trooper X4.0 | Trooper X4.0 | Mobiwire | Michael | Fred | MT6572 | 4.2.2 |  |  | 2014-Feb | 2014-Jan-01 | no |  |  |  |  | 1st Launch date:2013-Oct
Trooper X4.5 | Trooper X4.5 | Konka | Michael | Fred | MT6572 | 4.2.2 |  |  | 2014-Feb | 2014-Jan-01 | no |  |  |  |  | 2013-Oct
Thunder Q4.5 | Thunder Q4.5 | Regantek | Johnlai | Barry | MT6582M | 4.2.2 |  |  | 2014-Feb | 2014-Jan-01 | no |  |  |  |  | 1st Launch date: 2013-Dec-30 SW09
Trooper X5.0 | Trooper X5.0 | Konka | Michael | Fred | MT6572 | 4.2.2 |  |  | 2014-Feb | 2014-Jan-01 | no |  |  |  |  | 1st launch date:2013-Oct
Trooper X5.5 | Trooper X5.5 | Mobiwire | Michael | Fred | MT6572 | 4.2.2 |  |  | 2014-Feb | 2014-Jan-01 | no |  |  |  |  | 1st Launch date:2013-Oct
Trooper2 4.0 | Trooper2 4.0 | Konka | Michael | Fred | MT6572AW | 4.2.2 | Open market | EU | 2014-Mar-10 | 2014-Jan-20 2pcs | yes | 2014-Feb-21 | 2014-Mar-07 |  | 2014-Mar-18 | SW07
Trooper2 6.0 | Trooper2 6.0 | Huaqin | Johnlai | Barry | MT6572AW | 4.2.2 | Open market | EU | 2014-Mar-12 | 2014-Feb-15 2pcs | yes | 2014-Feb-14 | 2014-Mar-10 |  | 2014-Mar-18 | SW10
Thunder2 4.5L | Thunder2 4.5L | K-Touch | Michael | Lambert | MSM8926 | 4.3 | Open market | EU | 2014-Mar-30 | 2014-Feb-15 4pcs | yes | 2014-Feb-14 | 2014-Mar-20 | 2014-Apr-23 |  | SW09
Thunder2 5.0 | Thunder2 5.0 | Konka | Michael | Fred | MT6582 | 4.2.2 | Open market | EU | 2014-Apr-07 | 2014-Mar-02 2pcs | yes | 2014-Apr-01 | 2014-Apr-18 | 2014-Apr-24 |  | SW07
Trooper2 5.0 | Trooper2 5.0 | Konka | Michael | Fred | MT6572AW | 4.2.2 | Open market | EU | 2014-Apr-07 | 2014-Mar-02 2pcs | yes | 2014-Mar-11 | 2014-Apr-02 | 2014-Apr-15 |  | SW06
Trooper2 4.5 | Trooper2 4.5 | FSJ | Johnlai | Alice | MT6572AW | 4.2.2 | Open market | EU | 2014-Apr-15 | 2014-Mar-10 2pcs | yes | 2014-Mar-07 | 2014-Apr-15 | 2014-Apr-23 |  | SW07
Tornado2 5.0 | Tornado2 5.0 | SGW | Johnlai | Lambert | MT6592 | 4.2.2 | Open market | EU | 2014-Apr-21 | 2014-Mar-16 2pcs | yes | 2014-Mar-12 | 2014-Apr-17 | 2014-Apr-24 |  | SW06
KAZAM TV 4.5 | KAZAM TV 4.5 | Sprocomm | Kelvin | Grant | BCM23550 | 4.4 | PLUS | Poland | 2014-Jul-30 | 2014-June-30 4pcs | yes | 2014-May-28 | 2014-Aug-27 |  | 2014-Sep-09 | SW10
Thunder 345 | Thunder 345 | Konka | Serena | Fred | MT6582M | 4.4 | Open market | EU | 2014-Jul-04 | 2014-June-04 2pcs | yes | 2014-Jun-05 | 2014-Aug-02 | 2014-Aug-06 |  | SW09
Thunder 345L | Thunder 345L | Mobiwire | Beryl | Barry | MT6582M | 4.4 | Open market | EU | 2014-Aug-28 | 2014-Jul-28 2pcs | yes | 2014-Jul-04 | 2014-Sep-02 |  | 2014-Sep-15 | SW07
Thunder 345 LTE | Thunder 345 LTE | Mobiwire | Beryl | Grant | MT6582M | 4.4 | PLUS | Poland | 2014-Aug-20 | 2014-Jul-20 1pcs | yes | 2014-Jul-03 | 2014-Aug-11 |  | 2014-Aug-15 | SW06
Thunder 347 | Thunder 347 | Longcheer | Serena | Lambert | MT6582 | 4.4 | Open market | EU | 2014-Jul-21 | 2014-Jun-21 2pcs | yes | 2014-Jun-10 | 2014-Aug-01 | 2014-Aug-07 |  | SW07
Thunder 350L | Thunder 350L | Mobiwire | Beryl | Barry | MT6582M | 4.4 | Open market | EU | 2014-Oct-15 | 2014-Sep-15 2pcs | yes | 2014-Sep-08 | 2014-Sep-10 |  | 2014-Sep-11 | SW04
Tornado 350 | Tornado 350 | Regantek | Johnlai | Fred | MT6592M | 4.4 | Open market | EU | 2014-Oct-30 | 2014-Sep-30 2pcs | yes | 2014-Aug-27 | 2014-Sep-05 | 2014-Sep-11 |  | SW04
Tornado 348 | Tornado 348 | Gionee | Beryl | Grant | MT6592 | 4.4 | Open market | EU | 2014-Nov-25 | 2014-Oct-25 2pcs | yes | 2014-Oct-15 | 2014-Oct-28 | 2014-Oct-29 |  | SW06
Tornado 348 | Tornado 348 | Gionee | Beryl | Grant | MT6592 | 4.4 | Play | Poland | 2014-Nov-15 | 2014-Oct-15 1pcs | yes | 2014-Nov-4 | 2014-Nov-19 |  | 2014-Nov-20 | SW04
Trooper 450 | Trooper 450 | Sprocomm | Serena | Fred | MT6582M | 4.4 | Open market | Spain | 2014-Dec-15 | 2014-Nov-15 2pcs | yes | 2014-Nov-4 |  | 2014-Dec-01 | 2014-Dec-02 | SW06
Trooper 450 | Trooper 450 | Sprocomm | Serena | Fred | MT6582M | 4.4 | Telefonica | Spain | 2014-Dec-15 | 2014-Nov-15 1pcs | yes | 2014-Nov-25 | 2014-Nov-25 |  | 2014-Dec-01 | SW02
Tornado 455L | Tornado 455L | Coship | Kelvin | Barry | MSM8916 | 4.4.4 | Open market | EU | 2015-Feb-16 | 2015-Jan-16 4pcs | yes | 2014-Dec-30 | 2015-Jan-13 | 2015-Feb-02 |  | SW04
Trooper 451 | Trooper 451 | CG mobile | Johnlai | Alice | SC7731 | 4.4 | Open market | EU | 2015-Mar-01 | 2015-Feb-01 2pcs | yes | 2014-Nov-28 | 2014-Dec-08 |  |  | SW02
Trooper 440L | Trooper 440L | Huiye | Beryl | Grant | MT6582M | 4.4 | Open market | EU | 2015-Feb-10 | 2015-Jan-10 2pcs | yes | 2014-Dec-30 | 2014-Dec-30 | 2015-01-07 |  | SW05
Trooper 450L | Trooper 450L | Huiye | Beryl | Lambert | MSM8916 | 4.4.4 | Open market | EU | 2015-Mar-30 | 2015-Feb-30 2pcs | yes | 2015-01-10 | 2015-Feb-05 | 2015-Feb-13 |  | SW08
Trooper 445L | Trooper 445L | Huiye | Beryl | Grant | MT6582M | 4.4 | Open market | EU | 2015-Mar-16 | 2015-Feb-16 2pcs | yes | 2015-01-10 | 2015-Mar-20 | 2015-Apr-03 |  | SW09 *
Trooper 455 | Trooper 455 | CG mobile | Johnlai | Alice | SC7731 | 4.4 | Open market | EU | 2015-Apr-15 | 2015-Mar-15 2pcs | yes | 2015-01-19 | 2015-Apr-03 | 2015-Apr-15 |  | SW05
Trooper 550 | Trooper 550 | Kingcomm | Johnlai | Fred | SC7731 | 4.4.2 | Open market | EU | 2015-Jun-27 | 2015-Apr 2pcs | yes | 2015-03-23 | 2015-Apr-30 | 2015-May-13 |  | SW04 *
Trooper 551 | Trooper 551 | Sprocomm | Kelvin | Barry | SC7731 | 4.4.2 | Open market | EU | 2015-Jun-15 | 2015-Apr 2pcs | yes | 2015-04-25 | 2015-Apr-30 |  | 2015-May-12 | SW02 drop
Trooper 540 | Trooper 540 | Sprocomm | Kelvin | Barry | SC7715 | 4.4.2 | Open market | EU | 2015-Jun-30 | 2015-Apr 2pcs | yes | 2015-04-16 |  | 2015-Apr-27 |  | SW02 *
Thunder 550 | Thunder 550 | Sunry | Jeffery | Grant | SC7731 | 4.4.2 | Open market | EU | 2015-Jul-30 | 2015-May 2pcs | yes |  | 2015-May-21 |  |  | SW02 *
Thunder 550L | Thunder 550L | Coosea | Beryl | Grant | MT6735 | 5.1 | Open market | EU | 2015-Aug-10 | 2015-May 4pcs | yes |  | 2015-Jul-31 | 2015-Aug-19 |  | SW07
Trooper 550L | Trooper 550L | HCT | Jeffery | Barry | MT6735 | 5.1 | Open market | EU | 2015-Aug-15 | 2015-Jul 4pcs | yes |  | 2015-Jul-31 | 2015-Aug-18 |  | SW05
Trooper 555 | Trooper 555 | Kingcomm | Serena | Fred | SC7731 | 4.4.2 | Open market | EU | 2015-Aug-30 | 2015-Apr 2pcs | yes |  | 2015-May-21 |  |  | SW01 *
Trooper 545 | Trooper 545 | CKT | Serena | Fred | SC7731 | 5.1 | Open market | EU | 2015-Aug-10 | 2015-Jul 2pcs | yes |  | 2015-Aug-07 | 2015-Aug-21 |  | SW05 drop
Trooper 555 | Trooper 555 | Kingcomm | Serena | Flora | SC7731 | 5.1 | Open market | EU | 2015-Dec | 2015-Dec 1pcs | yes |  | 2015-Dec-14 |  |  | SW02
Trooper 555 | Trooper 555 | Kingcomm | Kelvin | Flora | MT6580 | 5.1 | Open market | EU | 2016-May | 2016-Mar 2pcs | no
Trooper 650 | Trooper 650 | FSN | Kelvin | Flora | MT6580 | 5.1 | Open market | EU | 2016-May | 2015-Dec 2pcs | yes |  |  |  |  | SW05
Trooper 650 4G | Trooper 650 4G | Huiye | Beryl | Alice | MSM8909 | 5.1 | Open market | EU | 2016-Mar | 2015-Dec 4pcs | yes |  | 2016-Feb-23 |  |  | SW02

## TS
Project name | Model name | Vendor | PM | CPU | OS | Carrier | Country | Launch date | Sample deadline | Sample Ready(yes/no) | Sample date | SW build ready date | Google Approval date(First sw version | Google Approval date(final build) | Note
T700 | T700 | Techfaith | Sam Xiao | MT6589 | 4.2.2 | Open market | UK | 2014-Apr-07 | 2014-Mar-07 4pcs | yes | 2014-Apr-02 | 2014-Apr-02 |  | 2014-Apr-23
R200 | R200 | BS | Ethan Hao | MT6582 | 4.2.2 | Open market | UK | 2014-Sep-20 | 2014-Aug-20 2pcs | yes | 2014-Sep-06 | 2014-Sep-09 |  | 2014-Sep-12 | SW19